## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | kornipalli varshan | 2025-05-12 | Initial ASR model showed high Word Error Rate (WER) for Hindi speech due to data imbalance during training. | Sprint-1 | kornipalli varshan | Model Accuracy | Action Taken: Rebalanced training dataset with 70% English and 30% Hindi samples and retrained Whisper-Tiny model (Stage-2). | 2025-10-12 | closed | noticed improvement wer
2 | Priyanshi Raina | 2025-07-12 | Audio uploaded via microphone was recorded successfully but not saved correctly, resulting in no transcription output. | sprint-1 | Priyanshi Raina | Logical | Updated API response to return translated audio path and connected frontend audio player dynamically. | 20-12-2025 | Closed | recorded audio is preprocessed correctly
3 | kornipalli varshan | 14-12-25 | Initial evaluation only considered overall WER, which did not reflect language-wise performance differences. | sprint-2 | kornipalli varshan | analytical | Implemented separate evaluation for English WER and Hindi CER/WER to accurately measure multilingual performance. | 18-12-25 | closed | individual WER of both languages predominantly increased
4 | Etikala Akhila | 2025-03-12 | I designed and implemented the backend for the AI Speech Translator using FastAPI. The system supports microphone and audio file input, performs speech-to-text using the Whisper small.en model for improved accuracy, translates the detected text using Google Translator, and generates translated speech output using gTTS. Audio preprocessing and format standardization were handled using FFmpeg, ensuring stable and accurate audio translation. | Sprint-1 | Etikala Akhila | Maintainability | Backend logic implemented and optimized | 20-12-2025 | Closed | Backend working perfectly as expected
5 | Konijeti Gayathri | 25-12-2025 | Original text was not generated when uploading video files, as audio was not properly extracted from video input. | Sprint-3 | Konijeti Gayathri | Logical | Integrated FFmpeg-based audio extraction in backend to convert video input into WAV format before transcription using Whisper. | 30-12-2025 | closed | Working fine after integrating FFmpeg-based audio extraction for video input
6 | Anjali Kumari | 25-12-2025 | Original system workflow and module-wise explanation were unclear in the initial documentation, making it difficult to understand the end-to-end ASR pipeline and integration with translation and TTS modules. | Sprint 3 | Anjali Kumari | Documentation / Functional Clarity | Revised and structured complete project documentation with clear module-wise workflow, architecture diagrams explanation, and detailed development-to-deployment steps. Added clear description for Speech Recognition, Translation, and TTS modules. | 28/12/25 | closed | Documentation clarity improved; mentor and team able to clearly understand project workflow and module responsibilities.
7 | Priyanshi Raina | 2026-03-01 | Deployment attempt failed due to limited memory and incompatibility of trained model with cloud environment. | Sprint-4 | Priyanshi Raina | environment | Decided to keep trained model locally and use public Whisper model for deployment scenarios. | 2026-05-01 | closed | due to high ram dependency couldn't able to deploy and decided to keep it localhost
8 | Etikala Akhila | 23-12-2025 | I extended the application to support video file input and YouTube URLs by extracting audio using FFmpeg and yt-dlp. The backend was optimized for performance and reliability, and end-to-end testing was completed. The system now supports multiple input types (audio, video, YouTube), provides translated text output, downloadable translated audio files, and a clean user interface connected to the backend for complete functionality. | Sprint-2 | Etikala Akhila | Logical | Handled video and YouTube input separately using yt-dlp and changed Whisper model from base to small.en for better accuracy. | 2026-02-01 | Closed | Working correctly after backend changes and re-tested with audio, video, and YouTube inputs.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others